## SYSTEM PRODUCT BACKLOG
PROJECT PRODUCT BACKLOG |  |  |  | Assignment |  | STATUS KEY
# | Item | Priority | Status | Team Member | Sprint | OPEN
1 | Title Page | LOW | CLOSED | Whitley | 1 | CLOSED
2 | Table of Contents | LOW | CLOSED | Whitley | 1
3 | Section 1 Executive Summary with Narrative and Conclusions | MEDIUM | CLOSED | Asia | 1
4 | Company Background & Current Environment | HIGH | CLOSED | Asia | 1
5 | Problem Analysis (BPA, BPI, BPR) | HIGH | CLOSED | Asia | 1
6 | Proposed System Objectives and Constraints | HIGH | CLOSED | Erin | 1
7 | Expected Benefits | HIGH | CLOSED | Whitley | 1
8 | Context Diagram | HIGH | CLOSED | Jordan | 1
9 | Section 2 Executive Summary with Narrative and Conclusions | MEDIUM | CLOSED | Whitley | 2
10 | Use Case Diagram | LOW | CLOSED | Erin | 2
11 | Supplement Specifications (Non-Functional) | HIGH | CLOSED | Jordan | 2
12 | Section 3 Executive Summary with Narrative and Conclusions | MEDIUM | CLOSED | Whitley | 3
13 | Complete Data Flow Diagram Package | HIGH | CLOSED | Asia | 3
14 | Hardware and Software Specification | HIGH | CLOSED | Jordan | 3
15 | Navigation Diagram | HIGH | CLOSED | Whitley | 3
16 | Entity Relationship Diagrams | HIGH | CLOSED | Jordan | 3
17 | Program Plan showing logic and I/Os (IPO Chart with each program listed) | HIGH | CLOSED | Jordan | 3
19 | Section 4 Executive Summary with Narrative and Conclusions | MEDIUM | OPEN |  | 4
20 | Test Plans | HIGH | OPEN |  | 4
21 | Training Manual and/or Reference/Procedure Manual | HIGH | OPEN |  | 4
22 | Technical Manual | HIGH | OPEN |  | 4
23 | Section 5 Executive Summary with Narrative and Conclusions | MEDIUM | OPEN |  | 5
24 | Migration Plan (Business, Technical, People Readiness) | HIGH | OPEN |  | 5
25 | Personal Project Assessment (by each member) | HIGH | OPEN |  | 6
26 | Lessons Learned during the project (by group) | LOW | OPEN |  | 6
27 | Explanation of challenges, problems and discoveries | HIGH | OPEN |  | 6
28 | All Burndown Charts, All Backlogs, All Meeting Logs | HIGH | OPEN |  | 6
29 | Any other supporting documentation | HIGH | OPEN |  | ALL

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Decide on Company/Project | HIGH | CLOSED | Everyone | CLOSED
2 | Contact and Set-Up Meeting | MEDIUM | CLOSED | Asia
3 | Meet with Representative | MEDIUM | CLOSED | Asia
4 | Obtain all information for Sprint 1 | HIGH | CLOSED | Asia
5 | Create Context Diagram | HIGH | CLOSED | Erin
6 | Create Use Case Diagram | HIGH | CLOSED | Jordan
7 | Create Backlog | HIGH | CLOSED | Whitley
8 | Create Burn Down Chart | HIGH | CLOSED | Erin
9 | Complete PSPI | HIGH | CLOSED | Everyone
10 | Complete SCRUM Meeting Log | HIGH | CLOSED | Asia
11 | Create Presentation | HIGH | CLOSED | Everyone

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Executive Summary | MEDIUM | CLOSED | Whitley | CLOSED
2 | Update Use Case Diagram | LOW | CLOSED | Erin
3 | Non-Functional Requirements | HIGH | CLOSED | Jordan
4 | Figma | HIGH | CLOSED | Jordan
5 | Update Context Diagram | LOW | CLOSED | Jordan
6 | Update Burndown Chart | LOW | CLOSED | Erin
7 | Create Presentation | HIGH | CLOSED | ALL

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Executive Summary | MEDIUM | CLOSED | Whitley | CLOSED
2 | Data Flow Diagram Package | HIGH | CLOSED | Asia
3 | Hardware and Software Specification | HIGH | CLOSED | Erin
4 | Navigation Diagram | HIGH | CLOSED | Whitley
5 | Entity Relationship Diagram | HIGH | CLOSED | Jordan
6 | Program Plan (IPO Chart) | HIGH | CLOSED | Jordan
7 | Update Burndown Chart | HIGH | CLOSED | Erin
8 | Create Presentation | MEDIUM | CLOSED | ALL

## SPRINT 4 BACKLOG
SPRINT 4 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Executive Summary | MEDIUM | OPEN |  | CLOSED
2 | Test Plans | HIGH | OPEN
3 | Training Manual | HIGH | OPEN
4 | Technical Manual | HIGH | OPEN
5 | Update Burndown Chart | HIGH | OPEN
6 | Create Presentation | MEDIUM | OPEN | ALL

## SPRINT 5 BACKLOG
SPRINT 5 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Executive Summary | MEDIUM | OPEN |  | CLOSED
2 | Migration Plan | HIGH | OPEN
3 | Update Burndown Chart | MEDIUM | OPEN
4 | Create Presentation | MEDIUM | OPEN | ALL

## SPRINT 6 BACKLOG
SPRINT 6 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Personal Project Assessment | MEDIUM | OPEN |  | CLOSED
2 | Lessons Learned | MEDIUM | OPEN
3 | Explanation of challenges, problems, and discoveries | HIGH | OPEN
4 | ALL Charts, Backlogs, and Meeting Logs | HIGH | OPEN
5 | Other supporting documentation | MEDIUM | OPEN
6 | Create Presentation | MEDIUM | OPEN