## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | Decide on Company/Project | 5.33 | Day 1: 2; Day 3: 2; Day 5: 1.33 | Erin
2 | Contact and Set-Up Meeting | 2 | Day 5: 1.33; Day 6: 2.66 | Jordan | 30
3 | Meet with Representative | 4 | Day 6: 4 | Asia
4 | Obtain all information for Sprint 1 | 4 | Day 3: 2.66; Day 9: 1.33 | Whitley
5 | Create Context Diagram | 2 | Day 9: 0.66; Day 10: 1.33 |  | 30 | Total Team Time
6 | Create Use Case Diagram | 2 | Day 9: 0.66; Day 10: 1.33
7 | Create Backlog | 1.33 | Day 8: 1.33
8 | Create Burn Down Chart | 2.66 | Day 12: 1.33; Day 13: 1.33
9 | Complete PSPI | 2 | Day 12: 1.33; Day 13: 0.66
10 | Complete SCRUM Meeting Log | 3 | Day 1: 2; Day 3: 2; Day 5: 2; Day 8: 2; Day 10: 2; Day 12: 2
11 | Create Presentation | 2.33 | Day 9: 2; Day 11: 2.66; Day 12: 1.33; Day 13: 2; Day 14: 1.33
Remaining Effort |  | 30.65 | 26.65 | 26.65 | 19.99 | 19.99 | 15.33 | 8.67 | 8.67 | 5.34 | 0.69 | -3.97 | -6.63 | -12.62 | -16.61 | -17.94
Ideal Effort |  | 30.65 | 28.4607 | 26.2714 | 24.0821 | 21.8929 | 19.7036 | 17.5143 | 15.325 | 13.1357 | 10.9464 | 8.7571 | 6.5679 | 4.3786 | 2.1893 | 1.0658e-14

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | Executive Summary | 11 | Day 2: 2; Day 3: 4; Day 7: 2; Day 8: 2; Day 13: 1 | Erin | 8.04
2 | Update Use Case Diagram | 5.33 | Day 4: 2; Day 7: 1.33; Day 10: 2 | Jordan | 8.04
3 | Non-Functional Requirements | 6 | Day 4: 2; Day 7: 2; Day 10: 2 | Asia | 8.04
4 | Figma | 5 | Day 6: 2; Day 8: 2; Day 10: 1 | Whitley | 8.04
5 | Update Context Diagram | 2.83 | Day 3: 0.5; Day 4: 2; Day 7: 1.33 |  | 41.16 | Total Team Time
6 | Update Burndown Chart | 2 | Day 5: 0.5; Day 8: 0.5; Day 11: 1
7 | Create Presentation | 9 | Day 3: 4; Day 6: 1; Day 8: 2; Day 11: 1; Day 13: 1
|  |  | wday | thurs | fri | sat | sun | mon | tues | wday | thurs | fri | sat | sun | mon | tues
Remaining Effort |  | 41.16 | 41.16 | 39.16 | 30.66 | 24.66 | 24.16 | 21.16 | 14.5 | 8 | 8 | 3 | 1 | 1 | -1 | -1
Ideal Effort |  | 41.16 | 38.22 | 35.28 | 32.34 | 29.4 | 26.46 | 23.52 | 20.58 | 17.64 | 14.7 | 11.76 | 8.82 | 5.88 | 2.94 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
1 | Executive Summary | 5 | Day 9: 2; Day 17: 2; Day 21: 1 | Erin | 14.25
2 | Data Flow Diagram Package | 7 | Day 2: 1; Day 9: 4; Day 16: 1; Day 21: 1 | Jordan | 14.25
3 | Hardware and Software Specification | 9 | Day 2: 2; Day 10: 2; Day 12: 4; Day 21: 1 | Asia | 14.25
4 | Navigation Diagram | 5 | Day 7: 1; Day 18: 3; Day 21: 1 | Whitley | 14.25
5 | Entity Relationship Diagram | 5 | Day 13: 1; Day 19: 2; Day 21: 1 |  | 57 | Total Team Time
6 | Program Plan (IPO Chart) | 4 | Day 16: 1; Day 18: 2; Day 21: 1
7 | Standard Naming Conventions | 6 | Day 10: 3; Day 14: 2; Day 21: 1
8 | Update Project Plan | 4 | Day 2: 2; Day 16: 1; Day 21: 1
9 | Update Burndown Chart | 6 | bar: Day 9; Day 12; Day 14; Day 16; Day 20 to Day 21
10 | Create Presentation | 6 | Day 15: 4; Day 21: 2
Remaining Effort |  | 57 | 57 | 52 | 52 | 52 | 52 | 52 | 51 | 51 | 44 | 39 | 39 | 34 | 33 | 30 | 26 | 22 | 20 | 15 | 13 | 12 | 1
Ideal Effort |  | 57 | 54.2857 | 51.5714 | 48.8571 | 46.1429 | 43.4286 | 40.7143 | 38 | 35.2857 | 32.5714 | 29.8571 | 27.1429 | 24.4286 | 21.7143 | 19 | 16.2857 | 13.5714 | 10.8571 | 8.1429 | 5.4286 | 2.7143 | -1.8652e-14

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
Erin
Jordan
Asia
Whitley
[25 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Erin
Jordan
Asia
Whitley
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Erin
Jordan
Asia
Whitley
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 30
[18 empty] | Sprint 2 | 41.16
[18 empty] | Sprint 3 | 57
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 128.16 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0