## Sprints 1-6
MIS 4173
| Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
| Project start date: | 2025-01-13 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
| Scrolling increment: | 0 | time axis 2025-01-13 to 2025-03-09
| Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-13 to 2025-03-09
Sprint I: Project Proposal
| Decide on a Company/Project | Low Risk | Whitley, Asia, Erin, Jordan | 100% | 2025-01-15 | 17
| Contact and Set-Up Meeting | On Track | Asia | 100% | 2025-02-01 | 1
| Meet with Representative | On Track | Asia | 100% | 2025-02-01 | 1
| Obtain Info needed for Sprint 1 | Med Risk | Asia | 100% | 2025-02-02 | 1
| Initial Context Diagram | Med Risk | Erin | 100% | 2025-02-02 | 2
| Initial Use Case Diagram | Med Risk | Jordan | 100% | 2025-02-02 | 2
| Initial Product Backlog | Med Risk | Whitley | 100% | 2025-02-02 | 2
| Burn Down Chart | Goal | Erin | 100% | 2025-02-02 | 2 | 2025-02-02: 2; 2025-02-03: 2
| PSPI | High Risk | Whitley, Asia, Erin, Jordan | 100% | 2025-02-02 | 2
| SCRUM Meeting Log | Med Risk | Asia | 100% | 2025-02-02 | 1
| Create Presentation for Sprint 1 | High Risk | Whitley, Asia, Erin, Jordan | 100% | 2025-02-03 | 1
| Submit Sprint 1 | Milestone | Asia | 100% | 2025-02-05 | 1
| Present Sprint 1 | Milestone | Whitley, Asia, Erin, Jordan | 100% | 2025-02-05 | 1
Sprint 2
| Determine Non-Functional Requirements | Med Risk |  | 5% | 2025-02-11 | 2
| Update Context Diagram and Use Case Diagram | High Risk |  | 15% | 2025-02-11 | 2
| Update Product Backlog | High Risk |  | 15% | 2025-02-11 | 2
| Update Sprint 2 Backlog | High Risk |  | 15% | 2025-02-11 | 2
| Update Sprint 2 Burn Down Chart | High Risk |  | 15% | 2025-02-11 | 2
| Update Sprint 2 PSPI (Figma) | High Risk |  | 0% | 2025-02-11 | 2
| Update Project Plan (Gantt Chart) | High Risk | Whitley | 50% | 2025-02-11 | 2
| Create Presentation | High Risk | Whitley, Asia, Erin, Jordan | 0% | 2025-02-12 | 1
| Review Presentation | Low Risk | Whitley, Asia, Erin, Jordan | 0% | 2025-02-16 | 2
| Submit Sprint 2 | Milestone | Asia | 0% | 2025-02-18 | 1
| Present Sprint 2 | Milestone | Asia | 0% | 2025-02-18 | 1
Sprint 3
| Update Project Report | Med Risk |  | 0% | 2025-02-19 | 20
| Create DFDs (level 0 & level 1) | High Risk |  | 0% | 2025-02-20 | 17
| Determine Hardware and Software Specifications | High Risk |  | 0% | 2025-02-20 | 17
| Create Navigation Diagram | High Risk |  | 0% | 2025-02-20 | 17
| Create Entity-Relationship Diagram | High Risk |  | 0% | 2025-02-20 | 17
| Create Program Plan (IPO Chart) | High Risk |  | 0% | 2025-02-20 | 17
| Determine Standard Naming Conventions | High Risk |  | 0% | 2025-02-20 | 17
Update Product Backlog | Update Sprint 3 Backlog | Med Risk |  | 0% | 2025-03-07 | 2
| Update Sprint 3 Burn Down Chart | Med Risk |  | 0% | 2025-03-07 | 2
| Update Project Plan (Gantt Chart) | Med Risk |  | 0% | 2025-03-07 | 1
| Create Presentation | Goal |  | 0% | 2025-03-08 | 1
| Review Presentation | Low Risk |  | 0% | 2025-03-09 | 2
| Submit Sprint 3 | Milestone |  | 0% | 2025-03-11 | 1
| Present Sprint 3 | Milestone |  | 0% | 2025-03-11 | 1
Sprint 4
| Update Project Report | Med Risk | Whitley | 0% | 2025-03-12 | 1
| Create Test Plans | High Risk |  | 0% | 2025-03-12 | 16
| Create Training Manual | High Risk |  | 0% | 2025-03-12 | 16
| Create Technical Manual | High Risk |  | 0% | 2025-03-12 | 16
| Update Project Plan (Gantt Chart) | Milestone |  | 0% | 2025-03-28 | 1
| Update Product Backlog | Milestone |  | 0% | 2025-03-28 | 1
| Update Sprint 4 Backlog | High Risk |  | 0% | 2025-03-28 | 1
| Update Sprint 4 Burn Down Chart | High Risk |  | 0% | 2025-03-28 | 1
| Create Presentation | Med Risk |  | 0% | 2025-03-28 | 1
| Review Presentation | High Risk |  | 0% | 2025-03-29 | 2
| Submit Sprint 4 | Milestone |  | 0% | 2025-04-01 | 1
| Present Sprint 4 | Milestone |  | 0% | 2025-04-01 | 1
Sprint 5
| Update Project Report | Med Risk |  | 0% | 2025-04-02 | 1
| Create Migration Plan | High Risk |  | 0% | 2025-04-03 | 10
| Update Project Plan (Gantt Chart) | Med Risk |  | 0% | 2025-04-12 | 1
| Update Product Backlog | Med Risk |  | 0% | 2025-04-12 | 1
| Update Sprint 5 Backlog | Med Risk |  | 0% | 2025-04-12 | 1
| Update Sprint 5 Burn Down Chart | Med Risk |  | 0% | 2025-04-12 | 1
| Create Presentation | Goal |  | 0% | 2025-04-12 | 1
| Review Presentation | Low Risk |  | 0% | 2025-04-13 | 2
| Submit Sprint 5 | Milestone |  | 0% | 2025-04-15 | 1
| Present Sprint 5 | Milestone |  | 0% | 2025-04-15 | 1
Sprint 6
| Update Project Report | High Risk |  | 0% | 2025-04-16 | 1
| Personal Project Assessment | Med Risk |  | 0% | 2025-04-16 | 5
| Lessons Learned | Med Risk |  | 0% | 2025-04-16 | 5
| Explanation of challenges, problems, and discoveries | High Risk |  | 0% | 2025-04-16 | 5
| Finalize all burndown charts, backlogs, and meeting logs | Low Risk |  | 0% | 2025-04-21 | 5
| Finalize other supporting documents | Low Risk |  | 0% | 2025-04-21 | 5
| Create Presentation | Goal |  | 0% | 2025-04-21 | 1
| Review Presentation | Low Risk |  | 0% | 2025-04-22 | 2
| Submit Sprint 6 | Milestone |  | 0% | 2025-04-24 | 1
| Present Sprint 6 | Milestone |  | 0% | 2025-04-24 | 1

## Sprint 1
MIS 4173
Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
Project start date: | 2025-01-13 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 0 | time axis 2025-01-13 to 2025-03-09
Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-13 to 2025-03-09
Sprint I: Project Proposal
Decide on a Company/Project | Low Risk | Whitley, Asia, Erin, Jordan | 100% | 2025-01-15 | 17
Contact and Set-Up Meeting | On Track | Asia | 100% | 2025-02-01 | 1
Meet with Representative | On Track | Asia | 100% | 2025-02-01 | 1
Obtain Info needed for Sprint 1 | Med Risk | Asia | 100% | 2025-02-02 | 1
Initial Context Diagram | Med Risk | Erin | 100% | 2025-02-02 | 2
Initial Use Case Diagram | Med Risk | Jordan | 100% | 2025-02-02 | 2
Initial Product Backlog | Med Risk | Whitley | 100% | 2025-02-02 | 2
Burn Down Chart | Goal | Erin | 100% | 2025-02-02 | 2 | 2025-02-02: 2; 2025-02-03: 2
PSPI | High Risk | Whitley, Asia, Erin, Jordan | 0% | 2025-02-02 | 2
SCRUM Meeting Log | Med Risk | Asia | 100% | 2025-02-02 | 1
Create Presentation for Sprint 1 | High Risk | Whitley, Asia, Erin, Jordan | 100% | 2025-02-03 | 1
Submit Sprint 1 | Milestone | Asia | 100% | 2025-02-05 | 1
Present Sprint 1 | Milestone | Whitley, Asia, Erin, Jordan | 100% | 2025-02-05 | 1

## Sprint 2
MIS 4173
Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
Project start date: | 2025-01-13 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 0 | time axis 2025-01-13 to 2025-03-09
Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-13 to 2025-03-09
Sprint 2
Determine Non-Functional Requirements | Med Risk |  | 5% | 2025-02-11 | 5
Update Context Diagram and Use Case Diagram | High Risk |  | 15% | 2025-02-11 | 5
Update Product Backlog | High Risk |  | 15% | 2025-02-11 | 5
Update Sprint 2 Backlog | High Risk |  | 15% | 2025-02-11 | 5
Update Sprint 2 Burn Down Chart | High Risk |  | 15% | 2025-02-11 | 5
Update Sprint 2 PSPI (Figma) | High Risk |  | 0% | 2025-02-11 | 5
Update Project Plan (Gantt Chart) | High Risk | Whitley | 50% | 2025-02-11 | 5
Create Presentation | High Risk | Whitley, Asia, Erin, Jordan | 0% | 2025-02-12 | 1
Review Presentation | Low Risk | Whitley, Asia, Erin, Jordan | 0% | 2025-02-16 | 2
Submit Sprint 2 | Milestone | Asia | 0% | 2025-02-18 | 1
Present Sprint 2 | Milestone | Asia | 0% | 2025-02-18 | 1

## Sprint 3
MIS 4173
| Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
| Project start date: | 2025-01-13 |  |  |  |  | February | [13 empty] | March | [34 empty] | April
| Scrolling increment: | 34 | time axis 2025-02-16 to 2025-04-12
| Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-02-16 to 2025-04-12
Sprint 3
| Update Project Report | Med Risk |  | 0% | 2025-02-19 | 20
| Create DFDs (level 0 & level 1) | High Risk |  | 0% | 2025-02-20 | 17
| Determine Hardware and Software Specifications | High Risk |  | 0% | 2025-02-20 | 17
| Create Navigation Diagram | High Risk |  | 0% | 2025-02-20 | 17
| Create Entity-Relationship Diagram | High Risk |  | 0% | 2025-02-20 | 17
| Create Program Plan (IPO Chart) | High Risk |  | 0% | 2025-02-20 | 17
| Determine Standard Naming Conventions | High Risk |  | 0% | 2025-02-20 | 17
Update Product Backlog | Update Sprint 3 Backlog | Med Risk |  | 0% | 2025-03-07 | 2
| Update Sprint 3 Burn Down Chart | Med Risk |  | 0% | 2025-03-07 | 2
| Update Project Plan (Gantt Chart) | Med Risk |  | 0% | 2025-03-07 | 1
| Create Presentation | Goal |  | 0% | 2025-03-08 | 1
| Review Presentation | Low Risk |  | 0% | 2025-03-09 | 2
| Submit Sprint 3 | Milestone |  | 0% | 2025-03-11 | 1
| Present Sprint 3 | Milestone |  | 0% | 2025-03-11 | 1

## Sprint 4
MIS 4173
Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
Project start date: | 2025-01-13 |  |  |  |  | March | [20 empty] | April
Scrolling increment: | 58 | time axis 2025-03-12 to 2025-05-06
Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-03-12 to 2025-05-06
Sprint 4
Update Project Report | Med Risk | Whitley | 0% | 2025-03-12 | 1
Create Test Plans | High Risk |  | 0% | 2025-03-12 | 16
Create Training Manual | High Risk |  | 0% | 2025-03-12 | 16
Create Technical Manual | High Risk |  | 0% | 2025-03-12 | 16
Update Project Plan (Gantt Chart) | Milestone |  | 0% | 2025-03-28 | 1 | bar: 2025-03-28
Update Product Backlog | Milestone |  | 0% | 2025-03-28 | 1
Update Sprint 4 Backlog | High Risk |  | 0% | 2025-03-28 | 1
Update Sprint 4 Burn Down Chart | High Risk |  | 0% | 2025-03-28 | 1
Create Presentation | Med Risk |  | 0% | 2025-03-28 | 1
Review Presentation | High Risk |  | 0% | 2025-03-29 | 2
Submit Sprint 4 | Milestone |  | 0% | 2025-04-01 | 1 | bar: 2025-04-01
Present Sprint 4 | Milestone |  | 0% | 2025-04-01 | 1 | bar: 2025-04-01

## Sprint 5
MIS 4173
Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
Project start date: | 2025-01-13 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 0 | time axis 2025-01-13 to 2025-03-09
Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-13 to 2025-03-09
Sprint 5
Update Project Report | Med Risk |  | 0% | 2025-04-02 | 1
Create Migration Plan | High Risk |  | 0% | 2025-04-03 | 10
Update Project Plan (Gantt Chart) | Med Risk |  | 0% | 2025-04-12 | 1
Update Product Backlog | Med Risk |  | 0% | 2025-04-12 | 1
Update Sprint 5 Backlog | Med Risk |  | 0% | 2025-04-12 | 1
Update Sprint 5 Burn Down Chart | Med Risk |  | 0% | 2025-04-12 | 1
Create Presentation | Goal |  | 0% | 2025-04-12 | 1
Review Presentation | Low Risk |  | 0% | 2025-04-13 | 2
Submit Sprint 5 | Milestone |  | 0% | 2025-04-15 | 1
Present Sprint 5 | Milestone |  | 0% | 2025-04-15 | 1

## Sprint 6
MIS 4173
Team 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Whitley, Asia, Erin, Jordan
Project start date: | 2025-01-13 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 0 | time axis 2025-01-13 to 2025-03-09
Spring description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-13 to 2025-03-09
Sprint 6
Update Project Report | High Risk |  | 0% | 2025-04-16 | 1
Personal Project Assessment | Med Risk |  | 0% | 2025-04-16 | 5
Lessons Learned | Med Risk |  | 0% | 2025-04-16 | 5
Explanation of challenges, problems, and discoveries | High Risk |  | 0% | 2025-04-16 | 5
Finalize all burndown charts, backlogs, and meeting logs | Low Risk |  | 0% | 2025-04-21 | 5
Finalize other supporting documents | Low Risk |  | 0% | 2025-04-21 | 5
Create Presentation | Goal |  | 0% | 2025-04-21 | 1
Review Presentation | Low Risk |  | 0% | 2025-04-22 | 2
Submit Sprint 6 | Milestone |  | 0% | 2025-04-24 | 1
Present Sprint 6 | Milestone |  | 0% | 2025-04-24 | 1